## Slide 1: Schedule and budget
M. Krupa for the BPM team
HL-LHC BPM Design Review – 18/11/2020

## Slide 2: New HL-LHC BPMs
 | BPMQSTZA (A Type) | BPMQSTZB (B type) | BPMQSWZA/B | BPMQBCZA/B (D2 type) | APWL | BPTX | TOTAL
Series | 4 | 20 | 4 | 8 | 8 | 4 | 44
Spares | 2 | 2 | 2 | 2 | 2 | 1 | 9
Prototypes | 2 | 2 | 2 | 2 | 1 |  | 7

## Slide 3: BPM installation sequence
Cryogenic BPMs (A type, B type and D2) are installed by WP3, WP12 and WP13 during the cryomagnet assembly
  Responsibility share covered by memorandum EDMS 2105453
  BPMs are installed after cold tests of the magnet
  Beam screen must be inserted before BPM installation
  Needed-by dates driven by WP3 and WP12 schedules
Warm pick-ups (APWL, BPTX) are installed by WP13 during LS3
  Series delivery needed latest when the LHC de-installation is completed
The rest of the presentation focuses only on the cryogenic BPMs

## Slide 4: Beam screen insertion dates
WP12 BS insertion schedule from April 2020
WP3 and WP12 delays due to COVID-19 not implemented
WP12 agreed to update WP13 when the schedule changes
These are assumed as BPM needed-by dates
A type BPM | B type BPM |  |  |  |  | D2 BPM
Q1 | Q2 (1) | Q2 (2) | Q3 | CP | D1 | D2
16 Feb 24 | 29 Mar 24 | 28 Jun 24 | 03 Aug 23 | 05 Apr 22 | 16 Mar 23 | 04 Aug 22
02 Feb 24 | 19 Apr 24 | 27 Sep 24 | 29 Nov 23 | 03 Jun 22 | 30 Mar 23 | 29 Sep 22
12 Apr 24 | 03 May 24 | 29 Nov 24 | 28 Feb 25 | 02 Feb 23 | 28 Jul 23 | 12 Jan 23
12 Nov 24 | 24 May 24 | 16 Aug 24 | 28 Feb 25 | 16 Feb 23 | 27 Oct 23 | 29 Mar 23

## Slide 5: 3D models and drawings readiness
3D designs are ready for releasing manufacturing drawings for pre-series production preparation at CERN Workshop
  Only the A type and B type electrode design to be updated without any impact on the rest of the design
Some changes in the 3D models made over the last 3 months
  Feedback from thermal simulations
  Feedback from WP3 and WP12
Additional changes might be implemented as an outcome of the review and BINP technologist/workshop feedback
Existing drawings are sufficient for discussions with BINP

## Slide 6: Integration tests
WP13 is preparing “simplified” BPMs for integration and installation checks (e.g. aperture round instead of octagonal)
Representative interconnection mock-ups needed to validate BPM design, integration, alignment, and installation
  Ongoing discussion with WP3 and WP12 on schedule and possible tests – some COVID-related delays
WP3, WP12 and WP13 are checking details using 3D models
  Interface dimensions and tolerances
  Aperture transitions
  Welding and cutting machines
  Cryogenic cable routing and installation

## Slide 7: 316LN quantities
BPMs | Type A | Type B | D2 | TOTAL
Series (BINP) | 4 | 20 | 8 | 32
Spares (BINP) | 2 | 2 | 2 | 6
Pre-series (CERN) | 2 | 2 | 2 | 6
Blanks | Type A + Type B | D2 | TOTAL
Already procured | 4 + 4 | 4 | 12
To be procured | 4 + 20 + 2 | 8 + 1 | 35
spare blanks

## Slide 8: 316LN procurement
12 x 316LN blanks already purchased for CERN / BINP pre-series
Need 35 more blanks for series production - 2+ months lead time
Once the blanks are ordered, any significant change to the BPM dimensions will have a large impact on cost and delay production
Note freezing the blank dimensions approved by WP3, WP12, WP13, WP15 (EDMS 2395068)
Excess material:
  +5 mm radius: 4 mm (machining) + 1 mm (design change)
  +10 mm length: 2x4 mm (machining) + 2 mm (design change)
Any future changes with an impact on the blank dimensions will have to be approved on the HL-LHC level through an ECR
SMB/SSL already very advanced with the price enquiry

## Slide 9: Other material procurement
100 tungsten blocks procured through WP12 contract
  10 pre-series (already at CERN), 90 series
Waterjet-cut OF copper for aperture transitions will be procured through CERN Stores
  Good availability, short lead times
RF contacts for aperture transition procured through WP12
Fasteners, other standard components will be procured through standard channels
  Small cost, good availability, short lead times

## Slide 10: RF components procurement
RF feedthroughs for A type and B type BPMs
  Procurement ongoing, delays due to some design changes
Button electrodes for D2 BPMs
  Preliminary design ready, procurement to be launched in 2021
Cryogenic coaxial cables
  Preliminary routing done but will likely change
  Severe problems in the past, suppliers now more reliable
  Will be procured in a larger order with collimator BPM cables
Cryostat flanges
  Procurement to be launched in 2021

## Slide 11: Pre-series production
2 pre-series campaigns planned
  At CERN: 2 BPMs of each type (6 in total)
  At BINP: 2 BPMs of each type (6 in total)
CERN pre-series production will start when the design is frozen
  Everything that can be, will be subcontracted
  Electron-beam welding will be done in-house
CERN pre-series BPMs will be our safety margin in case of delays in series production – requires freezing the design!
To avoid excessive spares, compliant CERN pre-series units could be removed from the final BINP production quantities

## Slide 12: BINP collaboration
COVID-19 impact on BINP similar to CERN
  Only limited activities on-site, scientific staff working remotely
  We can progress with all pre-production work
Official travel between BINP and CERN unlikely anytime soon
  Visit to BINP necessary before green-lighting the series production
Communication with BINP ongoing
  Official collaboration contract has not been signed yet
  BINP informally approved our 316LN blank dimensions
  Regular zoom meetings to discuss pre-series preparation and production started in September
  Contract amendment to be updated with current schedule and APWL/BPTX included
Raw material for BINP pre-series is ready for shipping

## Slide 13: Budget
Budget presented at the PSM in August
  Total 1.646 MCHF, no issues identified
  88 kCHF requested as extra scope (BPTX) – to be presented to the TCC and approved through ECR
  Production cost will be an in-kind contribution from BINP
  Ongoing discussions if material cost can be (partly) in-kind too
Latest news
  Tungsten absorber – thermal link assembly likely to be done at CERN (existing know-how and production line): 25 kCHF
  Welding of cooling tubes to the BPM body also to be done at CERN: no precise cost estimate yet

## Slide 14: Review summary
3D designs of A type, B type and D2 BPMs are ready for releasing manufacturing drawings for pre-series production preparation
  Various simulations done or ongoing by relevant WPs
  Design optimisation done with EN/MME and TE/VSC
  Integration and interfaces checked using 3D models
  A type and B type electrode model to be updated (no impact on parts)
Functional spec for A type and B type circulated, D2 to be circulated soon
Studies done to validate the foreseen manufacturing methods
Discussions with BINP ongoing but final contract not yet signed
First BPM installation (CP magnet) scheduled in April 2022
  ~ 1 BPM per month until February 2025 (Q3 magnet)
WP13 goal for the review is to approve launching the pre-series production phase at CERN main workshop

## Slide 15: Thank you for your attention
Special thanks for contributing to all review presentations: P. Bestmann, N. Biancacci, F. Carra, F. Cerutti, N. Chritin, P. Costa Pinto, A. Demougeot, D. Duarte Ramos, G. Favres, H. Garcia Gavela, C. Garion, P. Garritty, M. Gonzalez de la Aleja, J. Hansen, G. Iadarola, N. Kos, A. Kurtulus, S. Pereira, L. Prever-Loiri, E. Rigutto, M. Sabate Gilarte, B. Salvant, F. Santangelo, K. Scibor, G. Skripka, J. Swieszek, M. Thiebert, A. Vande Craen, R. Veness, W. Vollenberg