## Slide 1: Constraints on MCBXFB/A from WP3 schedule: string and integration
E. Todesco
15 October 2020

## Slide 2: INTEGRATION
The short corrector MCBXFB is included in MQXFB (Q2) cold mass
  The MQXFB magnet cannot be tested vertically, therefore a cold mass has to be built including the corrector
  The option of testing MQXFB in stand alone mode costs ~100 kCHF additional of components and additional work – it was adopted for the first and second prototype to speed up the test
  Any quench during operation of the MCBXFB will probably quench the triplet during operation – and this should be avoided at all costs
  MCBXFB setting depends on misalignment – via the remote alignment system one could probably reduce the requirements to 75% of what we have today as nominal (1.8 T m in each plane, maximum torque of 56% of what we have today as nominal
The long corrector is included in the corrector package cold mass
  Previous consideration for quench are probably not valid in this case
  Its settings have a systematic component (the crossing angle) in one plane – the requirements can be lowered today to 4.5 and 2.5 T m in each plane (but with the freedom of leaving to operation to choose which plane) – therefore the nominal torque is already 56% of nominal
    These requirements could be further reduced including the remote alignment system

## Slide 3: STRING
We need two short correctors for the string
  We already have them, so this is ok
We need one long corrector, tested by July 2021
  3 months cold mass, two for cryostat, two for test (including Xmas), three for preparation for string (quite complex)

## Slide 4: OTHER Q2’s
Short corrector needed
  February 2021 (first Q2 for the string)
  April 2021 (second Q2 for the string, first MQXFB of the series)
  August 2021 (second MQXFB of the series – first for the tunnel)
  December 2021 (third MQXFB of the series – second for the tunnel) – this should come from the contractor
  Then, one every 5 months

## Slide 5: CRITICAL PATH
Today we have in the critical path
  June 2021 to have the coils for the long magnet ready for assembly
  December 2021 to have the magnet completed by the contractor, ready for test at CERN
They both look quite challenging, also considering
  The necessity of building two (or four) additional short inner layer coils
  The usual very long time that takes for a contractor to start the production
We should define actions to minimize these risks
  Double shift/parallel work in CIEMAT
  Strategy for transfer from CIEMAT to industry
Tentative priority list
  Tender has the top priority (asap)
  Order the tooling for shorter coils in MCBXFB (asap)
  Apply the tooling change to the MCBXFA
  Define the strategy for the sequence of next coils at CIEMAT (short / new shorter / long)
  Conclude the simulation and analysis, with a dedicated technical meeting (mid November)
  I would still insist to explore the limits to increase preload in P2 with an additional assembly (to be discussed)