Talk Title
NDGF dCache 1.8 upgrade
Oxana Smirnova / Gerd Behrmann
November 6th 2007
CERN

---
NDGF dCache setup
5 sites
UiB, UiO, NBI, CSC, HPC2N
56 pools on 15 hosts
243 TB
SRM, XROOTD
2xGridFTP

---
Monday, October 29th
08:00 downtime officially starts
08:30 dcache pools are set rdonly
09:00 we take down central dcache instance for upgrades
09:00 rls@uppsala shuts down and a database dump is created
09-10 while dcache is down, all pools stop and begin the upgrade
  - UiO replaced NIC with 10 Gig Ethernet
  - UiB reconfigured FC multipathing
11:00 testing of the central services at örestaden (dcache+rls)
12:00 rls and central dcache services online
12-16 pools coming online, by 16 enough should be online to accept writes
16-08 spare time for delays, rest of pools coming online
09:00 whole-system verification that everything works as intended
10:00 downtime officially over

---
How did it go?
Most things went as planned!
UiB had to delay Fibre Channel multipathing.
UiO needed more time than expected for the NIC upgrade, but the pools were online around 1800.
RLS required some additional configuration steps (authentication, setting auto-increment fields in the DB after import).
dCache 1.8-0 FTP bug caused ARC client to fail. Was fixed within the hour and rolled out on the FTP doors. Fix is included in dCache 1.8-1.
Initial problems at UiO with new Berkeley DB based repository code. Was eventually tracked down to a weird interaction between the Java GC and a some new caching code in dCache. The cache was removed, and everythings works fine now.

---
Space Reservation
Initially not enabled, as the upgrade to dCache 1.8 was enough risk for one day.
Will be enabled soon – likely this week – using implicit space reservations.
Unsure whether we should create static DISK and TAPE reservations for Atlas:
  - How big should they be? Bear in mind that the reserved space will be unavailable for “old transfers”.
  - What exactly was the use case for those reservations (compared to having the disk/ and tape/ directories)?
  - Could ATLAS create those reservations themselves?
ARC clients do not yet support SRM 2.2.