## Slide 1
Hardware commissioning schedule
RF agenda during hardware commissioning phase
Detailed online schedule at https://oss-coordination.web.cern.ch/gantt/latest

## Slide 2
Racks for Finemet cavity (b. 151) exchanged
  Re-cabling/testing of coupled-bunch feedback ongoing
  Synchronization tests  Jan
Timing and function installation 20 MHz, 40 MHz and 80 MHz
  Installation and configuration completed
  Hardware restart timings (PAX.SBRH84/168) cabled to b. 151
  MakeRules for duplicated timings PAX.WV80, PAX.SAVCC80
Remaining cabling
  PA.GSVPC78
  Distribution of stable phase, fS program PA.GSPPROGRT
    Replace APP (Automatic Phase Program) module
  Function to control phase loop gain PA.GSPLGAIN(RT)
    Lower gain before injection (and at h = 84)
  Final validation of phase program and phase loop gain pending
Status of activities in PS CB and nearby (b. 151)

## Slide 3
  RF CPS eLogbook: http://elogbook.cern.ch/eLogbook/eLogbook.jsp?lgbk=382
  Ongoing and next steps
  Wall current monitor (WCM95) distribution  Ben, Pierre
    Replacement of aging distribution amplifiers
  Digital cavity controller 40 MHz and 80 MHz power systems  Ben
    Multi-harmonic feedback working
    Controls request: phase and tuning functions, acquisition timings
  2 GeV cycle with appropriate timing tree  Denis, Heiko
    BCMS setting-up
    Test of cavities with pre-/post LS2 next week
Re-commissioning of LLRF equipment

## Slide 4
  RF CPS eLogbook: http://elogbook.cern.ch/eLogbook/eLogbook.jsp?lgbk=382
  Ongoing and next steps
  10 MHz cavities
    Checks of cavity returns signals (eLogbook)
    9/11 cavities pulsing on pre-LS2 BCMS
  Christmas break
    No cooling water ‘eau glacée’ for air conditioning
    Stop NIM and LHC-RF VME crates before closure
  Week 1 in 2021
    04-07/01 Controls maintenance days (‘Note de Coupure’)
    07-08/01 Final RF bypass check (with magnet covers) in PS switchyard
Re-commissioning of LLRF equipment