## Slide 1: AD-CONS / ELENA Projects
ADUC 19th January 2021
AD facility consolidation
François BUTIN – BE-EA

## Slide 2
November 2018
August 2020
ELENA
New TL’s
installation
25 AD ring magnets refurbished
PUMA new TL + exp area design
30 t dipole extraction
LNE51 TL
PUMA new exp area
BHW09
ELENA
Ring + TL’s
Run-in
Beam profiles in TL’s
ELENA ring
2020 Highlights at AD

## Slide 3: AD-CONS WP’s
-Magnets refurbishment:
-status: LS2 program is complete, will continue till LS3 included
-Difficulties: extraction uneasy, many concrete blocks moved in tight environment
-Next: evaluate possibilities during (short) YETS 21-22 (2 quads, QDN12 and 13 ?)
-RF systems:
-Status: C02 cavity replaced by Finemet type (from PSB), LLRF integration with ELENA, C10 tubes being replaced
-Difficulties: qualified personnel availability in concurrence with PSB, LEIR
-Next: evaluate C10 future operation, review long term needs, extra budgets likely needed
-Vacuum:
-Status: ion pumps replacement: complete
-Difficulties: bake-out planning in concurrence with LHC
-Next: complete, no more needs foreseen
-AD e-cooler:
-Status: collector replacement production complete, tests in progress, some delays
-Difficulties: uncertainty on availability in time
-Next: decide on installation of new collector in April 21, depending on delays
New Finement cavity

## Slide 4: AD-CONS WP’s (Continued)
-Stochastic cooling:
-Status: amplifiers re-installation in progress
-Difficulties: no visibility on program till and including LS3 (pick-up + kicker refurbishment likely needed), loss of knowledge
-Next: review project, date, define budgets needed
-Target renovation:
-Status: in progress
-Difficulties: some delays COVID related, impact on physics restart
-Next: Commissioning expected to start in June 2021
-Cryo distribution system:
-Status: project launched, fellow started gathering info and designing system
-Difficulties: get adequate priority level withing CRG projects
-Next: get technical spec in summer 2021
-Cooling and ventilation:
-Status: stalled
-Difficulties: get required priority level
-Next: refine cost estimates, get project schedule for summer 2021
Stoch cooling

## Slide 5: AD-CONS WP’s (continued)
-AD cranes refurbishment:
-Status: planned for 2022-2023
-Difficulties: none
-Next: review project end 2021
-Magnetic Horn:
-Status: complete
-Difficulties: none
-Next: power cables and transmission line were mentioned as additional work, but not confirmed
-AD-CONS project management:
-Status: WPs update summary document ready, distributed in Eng check
-Project Management Plan document ready to be circulated for Eng check
-C&S review to be planned for 2021

## Slide 6: Ring magnets refurbishment
2 bending
2 bending
2 bending + 1 quad
2 bending + 1 quad
1 bending
3 Quads
2 bendings
1 Quad
1 bending + 4 quads
1 Quad
1 bending + 1 quad + 1 septum
YETS 21-22 2 Quads
Work consists in opening magnets, replace shimming , check insulation, cooling, connectors,
Perform measurement and certification
All connections will now be protected to be IP3 (fully exposed till now)

## Slide 7: Context 2021 restart …and stop
DRAFT !
MY GUESS ONLY !!!

## Slide 8: Aegis exp area improvement
New wall to protect
Aegis exp area

## Slide 9: LNE02 (Aegis) TL installation
Missing
transition piece + valve
Exp end January

## Slide 10: PUMA exp area installation
PUMA is approved at AD
Experimental area being installed, expected complete in April
New transfer line LNE51 installation about to start, expected complete in July – connection to ELENA ring in November
Start of experiment components installation as of Autumn
PUMA trap delivery date to be confirmed

## Slide 11: STEP status
STEP not yet approved, but soon !
Encouraged to start preparing exp area
Site of ex-ATRAP1 chosen (LNE01 ELENA transfer line)
Detailed installation planning to be clarified
Aiming at pbars trapping in 2023
STEP location
Transfer gate

## Slide 12: Also on 2021 menu
New platform
(PUMA / BASE / ASACUSA)
Spring 21
ASACUSA barrack
Remodelling
YETS 21-22
ALPHA barrack
YETS 22-23
BIG cleaning of AD hall initiated
-ELENA zone done
-Remaining zones in February
-PLEASE CLEAR AS MUCH STUFF
as possible to make the cleaning
process effective

## Slide 13: ATRAP space re-allocation
Converging to an approved doc
Only snagging point is access to platform above ex-ATRAP laser room
Proposed to be from ASACUSA rack platform
Laser room
New stairs
Storage platform