## Slide 1
2021 accelerator schedule: Q1-Q2
Presented by R. Steerenberg in IEFC, IPP, FOM, approved by SPSC

## Slide 2
Items to completed/prepared before start with beam
  Pulse 40 MHz cavity: early February
    Digital cavity controller together
    AVC surveillance prototype module
    Need clear path for operational roll out during 2021 run
  Pulse 200 MHz system with mTCA controller: February
    Proof-of-principle with prototypes
    Validate mTCA cavity controller
    Define strategy for operational implementation in YETS21/22
  Prepare phase measurement of digital beam control: March
    Open loop phase between beam and 10 MHz cavity vector sum
    Two harmonic simultaneously
    Following harmonic number changes
    Validate major parts of digital beam control
Main priorities for early 2021

## Slide 3
Coupled-bunch feedback
  Re-cabling/testing of coupled-bunch feedback ongoing
  Synchronization tests  Jan
Barrier bucket generation
  To be re-cabled  Mihaly
Remaining cabling
  PA.GSVPC78
  Distribution of stable phase, fS program PA.GSPPROGRT
    Replace APP (Automatic Phase Program) module
  Function to control phase loop gain PA.GSPLGAIN(RT)
    Lower gain before injection (and at h = 84)
  Phase program and phase loop gain functions ready
  MakeRule for virtual start-stops, transition and scaling to be completed  Denis
Status of activities in PS CB and nearby (b. 151)

## Slide 4
  RF CPS eLogbook: http://elogbook.cern.ch/eLogbook/eLogbook.jsp?lgbk=382
  Ongoing and next steps
  Wall current monitor (WCM95) distribution  Ben, Pierre
    Replacement of aging distribution amplifiers
  Digital cavity controller 40 MHz and 80 MHz power systems  Ben
    Multi-harmonic feedback working
    Controls request: phase and tuning functions, acquisition timings
  2 GeV cycle with appropriate timing tree  Denis, Heiko
    BCMS setting-up
    Cavities pulsing with pre-/post LS2 cycles
  Cycle timing tree and function generation for other cycles  Denis, Heiko
    TOF (TREEH8)  MTE (TREEH8H16)
    Conventional LHC (triple splitting only, TREEH21)
Re-commissioning of LLRF equipment

## Slide 5
  RF CPS eLogbook: http://elogbook.cern.ch/eLogbook/eLogbook.jsp?lgbk=382
  Ongoing and next steps
  10 MHz cavities
    Cavity returns signals all delivering signals (eLogbook)
  Recovery from Christmas break
    Cooling water ‘eau glacée’ back on 04/01
    Equipment back on 07/08
      Two broken NIM power supplies replaced
      cfv-151-allbbcwb has no clock yet  Mihaly
      SVEC in cfv-353-allrfp2 in boot loop  Nathan
    First 10 MHz cavities pulsing again
  Week 1 in 2021
    04-07/01 Controls maintenance days (‘Note de Coupure’)
    07-08/01 Final RF bypass check (with magnet covers) in PS switchyard
Re-commissioning of LLRF equipment

## Slide 6
  RF CPS eLogbook: http://elogbook.cern.ch/eLogbook/eLogbook.jsp?lgbk=382
  Ongoing and next steps
  Extraction train distribution  Diego
    Lab tests well advanced (non-blocking issue with fsync measurement)
    Move front-end to b. 353 in week 3 and connect
  AVC surveillance  Stephane
    Completion of prototype firmware and lab tests
    Interlock check with power system: week 4
    Tests with C40-77: weeks 5/6
  200 MHz AVC loop  Matteo
    1st 200 MHz cavity to be handed over by RF-AC on 29/01, all on 12/02
    Completion of prototype firmware and lab tests
    Tests with single 200 MHz cavity week 6
  Final preparation of LLRF for beam week 7/8
Re-commissioning of LLRF equipment

## Slide 7
Hardware commissioning schedule
RF agenda during hardware commissioning phase
Detailed online schedule at https://oss-coordination.web.cern.ch/gantt/latest

## Slide 8
LS2 feedback and activities for YETS2021-22
LS2 feedback for ISTs and HWC
  Extremely useful to have clear agenda for availability of services: air conditioning and electricity
  IST period allowed to perform many checks at an early stage
  Planning when other systems required signals from LLRF
  Difference IST/HWC not fully clear for LLRF systems: outside ring with no impact on safety
  Online schedule (https://oss-coordination.web.cern.ch/gantt/latest)
    Overwhelming for non-experts, difficult to browse
  System validation too early with respect to operational
    ‘OK when tested, already broken when really needed’
EYETS2021/22 activities
  Installation of digital cavity controllers on all 200 MHz systems
    Services in b. 151 and 5 days of power tests with cavities
  Fix items discovered during 2021 run
    Expect minor cabling and installation of LLRF modules in b. 353
Joint Coordination Meeting for the PS Complex